## Sheet1
Date | time axis 2023-10-28 to 2025-08-31
Description | Plan/ Actual | Unit
General items
Establishment, Maintenance and Reinstatement
Office site
Site clearance | P
Site clearance (1.1.1.1) | A | sq.m
Fence (external) | P
Fence (external) (1.1.1.2) | A | lin.m
Fence (internal) | P
Fence (internal) (1.1.1.3) | A | lin.m
Internal access road | P
Internal access road (1.1.1.4) | A | sq.m
Internal drainage system | P
Internal drainage system (1.1.1.5) | A | lin.m
Contractor's Temporary Buildings and Facilities | P
Contractor's Temporary Buildings and Facilities (1.1.1.6) | A | LS
Maintenance of office site | P
Maintenance of office site (1.1.1.7) | A | Month
Employer's and Engineer's facilities
Provision of mini-bus for the Employer/Engineer | P
Provision of mini-bus for the Employer/Engineer (1.1.2.1) | A | Vehicle Month
Provision of pick-up for the Employer/Engineer | P
Provision of pick-up for the Employer/Engineer (1.1.2.2) | A | Vehicle Month
Provision of 4WD for the Employer/Engineer | P
Provision of 4WD for the Employer/Engineer (1.1.2.3) | A | Vehicle Month
Provision of drivers for the Employer/Engineer | P
Provision of drivers for the Employer/Engineer (1.1.2.4) | A | Man Month
Site laboratory
Provide and Remove Site Laboratory | P
Provide and Remove Site Laboratory (1.1.3.1) | A | LS
Provide and Remove Laboratory equipment | P
Provide and Remove Laboratory equipment (1.1.3.2) | A | LS
Operation & Maintenance of laboratory | P
Operation & Maintenance of laboratory (1.1.3.3) | A | Month
Others
Project information board | P
Project information board | A | LS
Monthly progress report, progress photographs and videos | P
Monthly progress report, progress photographs and videos (1.1.4.2) | A | Month
Perimeter fence with coiled razor wire on top in Depot | P
Perimeter fence with coiled razor wire on top in Depot (1.1.4.3) | A | lin.m
Site survey
Provision of survey instruments and equipment to Engineer | P
Provision of survey instruments and equipment to Engineer (1.2.1) | A | LS
Verification survey of given bench mark | P
Verification survey of given bench mark (1.2.2) | A | LS
Maintenance of existing roads during construction
Survey of road surface of existing roads along project | P
Survey of road surface of existing roads along project (1.3.1) | A | lin.m
Fence along with existing road in the Depot (Establishment, Maintenance and Reinstatement) | P
Fence along with existing road in the Depot (Establishment, Maintenance and Reinstatement) (1.3.2) | A | lin.m
Repair of potholes | P
Repair of potholes (1.3.3) | A | cu.m
Repair of broken edge | P
Repair of broken edge (1.3.4) | A | lin.m
Repair of cracking | P
Repair of cracking (1.3.5) | A | sq.m
Repair of rutting | P
Repair of rutting (1.3.6) | A | sq.m
Repair of depression | P
Repair of depression (1.3.7) | A | sq.m
Leveling | P
Leveling (1.3.8) | A | sq.m
Overlaying | P
Overlaying (1.3.9) | A | ton
Utility location investigation
Trial pit (L2.0mxW1.5mxD2.0m) | P
Trial pit (L2.0mxW1.5mxD2.0m) (1.4.1) | A | nos.
Trial trench (W1.5mxD2.0m) | P
Trial trench (W1.5mxD2.0m) (1.4.2) | A | lin.m
Security, Safety and Health
Security, Safety and Health (first aid) goods | P
Security, Safety and Health (first aid) goods (1.5.1) | A | LS
Security, Safety and Health (first aid) practice | P
Security, Safety and Health (first aid) practice (1.5.2) | A | LS
Site clearing and temporary drainage system
Clearing and grubbing
Clearing and grubbing | P
Clearing and grubbing (2.1.1) | A | sq.m | 2023-10-29: 4965
Removal of existing structure
Cutting, transportation and disposal of existing trees | P
Cutting, transportation and disposal of existing trees (2.2.1) | A | nos
Earth work
Excavation
Excavation | P
Excavation (3.1.1) | A | cum | 2023-10-28: 1300; 2023-10-29: 220; 2023-11-01: 140; 2023-11-02: 320; 2023-11-03: 540; 2023-11-04: 360; 2023-11-06: 520; 2023-11-07: 300; 2023-11-08: 240; 2023-11-09: 340; 2023-11-10: 280; 2023-11-11: 1300; 2023-11-12: 380; 2023-11-13: 420; 2023-11-14: 520; 2023-11-15: 880; 2023-11-16: 1140; 2023-11-20: 100; 2023-11-21: 640; 2023-11-22: 840; 2023-11-23: 820; 2023-11-24: 700; 2023-11-25: 740; 2023-11-26: 800; 2023-11-27: 1240; 2023-11-28: 980; 2023-11-29: 1180; 2023-11-30: 1140; 2023-12-01: 1140; 2023-12-02: 1200
Filling
Filling up to MSL 5.5m | P
Filling up to MSL 5.5m (3.2.1) | A | cum | 2023-10-29: 1129; 2023-10-30: 508; 2023-11-01: 593; 2023-11-03: 282; 2023-11-05: 114; 2023-11-07: 621; 2023-11-08: 857.43; 2023-11-09: 835; 2023-11-10: 993.19; 2023-11-11: 632.03; 2023-11-12: 542; 2023-11-14: 1015
Sand mat (between MSL 5.5m and 6.0m) | P
Sand mat (between MSL 5.5m and 6.0m) (3.2.2) | A | cum | 2023-10-30: 916; 2023-11-02: 1580; 2023-11-03: 1817; 2023-11-04: 378; 2023-11-09: 1501; 2023-11-10: 2670.3; 2023-11-11: 679; 2023-11-12: 1259; 2023-11-13: 1422; 2023-11-14: 837.44; 2023-11-15: 3587; 2023-11-16: 838; 2023-11-20: 474; 2023-11-21: 1011; 2023-11-22: 348; 2023-11-26: 316; 2023-12-02: 221
Embankment (above MSL 6.0m) | P
Embankment (above MSL 6.0m) (3.2.3) | A | cum | 2023-11-15: 1140; 2023-11-16: 1524; 2023-11-18: 666; 2023-11-19: 2291; 2023-11-20: 2201; 2023-11-21: 1772; 2023-11-22: 2528; 2023-11-23: 3228; 2023-11-24: 2991; 2023-11-25: 2077; 2023-11-26: 1840; 2023-11-28: 3171; 2023-11-30: 2299; 2023-12-01: 2157; 2023-12-02: 2573
Geosynthetic-reinforcement | P
Geosynthetic-reinforcement (3.2.4) | A | sq.m | 2023-11-05: 2200; 2023-11-06: 2280; 2023-11-07: 4775; 2023-11-08: 8064; 2023-11-09: 8257.34; 2023-11-10: 7049.4; 2023-11-11: 5751.02; 2023-11-13: 3575.28; 2023-11-14: 9173.13; 2023-11-15: 8772.85; 2023-11-16: 1767.42; 2023-11-20: 3572.4; 2023-11-21: 4802.27; 2023-11-22: 8288.91; 2023-11-23: 7793.4; 2023-11-24: 7702; 2023-11-25: 5126; 2023-11-27: 3070; 2023-11-28: 2680.27; 2023-11-29: 2167
Horizontal drainage
Crushed stones | P
Crushed stones (3.3.1) | A | cum
Nonwoven fabric | P
Nonwoven fabric (3.3.2) | A | sq.m
Gabion | P
Gabion (3.3.3) | A | cum
Slope protection
Vegetation
Geotextile filter | P
Geotextile filter (4.1.1) | A | sq.m
Clay blanket (300mm thick) | P
Clay blanket (300mm thick) (4.1.2) | A | sq.m
Turfing | P
Turfing (4.1.3) | A | sq.m
Gabion
Gabion (at embankment toe of water pond area) | P
Gabion (at embankment toe of water pond area) (4.2.1) | A | cum
Soil improvement
Soil improvement
Static Sand Compaction pile | P
Static Sand Compaction pile (5.1.1) | A | lin.m | 2023-10-28: 422; 2023-10-29: 925.5; 2023-10-30: 1334; 2023-11-01: 1019; 2023-11-02: 968.5; 2023-11-03: 233.5; 2023-11-04: 939; 2023-11-05: 1272.5; 2023-11-06: 1323.5; 2023-11-07: 1204; 2023-11-08: 1304; 2023-11-09: 1219.5; 2023-11-10: 322.5; 2023-11-11: 940.5; 2023-11-12: 1335; 2023-11-13: 967; 2023-11-14: 1199.5; 2023-11-15: 1242.5; 2023-11-16: 1280; 2023-11-17: 204.5; 2023-11-18: 1293.5; 2023-11-19: 1185.5; 2023-11-20: 1381.5; 2023-11-21: 1308.5; 2023-11-22: 1380; 2023-11-23: 1293.5; 2023-11-25: 1370; 2023-11-26: 1419.5; 2023-11-27: 1442; 2023-11-28: 1402.5; 2023-11-29: 1545; 2023-11-30: 1429.5; 2023-12-01: 0; 2023-12-02: 1428
Vibrating Sand Compaction Pile | P
Vibrating Sand Compaction Pile (5.1.2) | A | lin.m | 2023-10-28: 378; 2023-10-29: 1210.5; 2023-10-30: 1635; 2023-11-01: 1458; 2023-11-02: 1591; 2023-11-03: 503; 2023-11-04: 1119.5; 2023-11-05: 1545; 2023-11-06: 1759.5; 2023-11-07: 1728; 2023-11-08: 1730; 2023-11-09: 1606.5; 2023-11-10: 460.5; 2023-11-11: 1200.5; 2023-11-12: 1263.5; 2023-11-13: 1201.5; 2023-11-14: 1084; 2023-11-15: 1511; 2023-11-16: 1387.5; 2023-11-17: 258; 2023-11-18: 1459.5; 2023-11-19: 1599.5; 2023-11-20: 1257.5; 2023-11-21: 1762.5; 2023-11-22: 1500; 2023-11-23: 1457.5; 2023-11-25: 1427.5; 2023-11-26: 1294; 2023-11-27: 1363.5; 2023-11-28: 1475; 2023-11-29: 1449; 2023-11-30: 1402; 2023-12-01: 0; 2023-12-02: 1268
Standart Penetration Test for SCPs | P
Standart Penetration Test for SCPs (5.1.3) | A | nos | 2023-11-14: 10; 2023-11-15: 10; 2023-11-19: 20; 2023-11-20: 10; 2023-11-21: 10; 2023-11-23: 10; 2023-11-24: 10; 2023-11-25: 10; 2023-11-26: 10; 2023-11-27: 20; 2023-11-28: 10; 2023-11-29: 10; 2023-11-30: 10; 2023-12-01: 10; 2023-12-02: 10
Prefabricated Vertical Drain | P
Prefabricated Vertical Drain (5.1.4) | A | lin.m | 2023-10-28: 15.28; 2023-10-29: 1400; 2023-10-30: 400
Surcharge at PVD area(Filling & Removal) | P
Surcharge at PVD area(Filling & Removal) (5.1.5) | A | cu.m
Monitoring of settlement and horizontal movement
Monitoring of settlement and horizontal movement
Installment of settlement plate and gauge | P
Installment of settlement plate and gauge (6.1.1) | A | nos
Installment of inclinometer | P
Installment of inclinometer (6.1.2) | A | nos
Installment of wood stake | P
Installment of wood stake (6.1.3) | A | nos
Measurement of settlement by settlement plate | P
Measurement of settlement by settlement plate (6.1.4) | A | nos-month
Measurement of horizontal deformation | P
Measurement of horizontal deformation (6.1.5) | A | nos-month
Measurement of settlement by wood stake | P
Measurement of settlement by wood stake (6.1.6) | A | nos-month
Drainage
Excavation for drainage work
Excavation for drainage work | P
Excavation for drainage work (7.1.1) | A | cu.m | 2023-11-05: 150; 2023-11-13: 175; 2023-11-20: 55; 2023-11-21: 80; 2023-11-22: 27; 2023-11-23: 110.4; 2023-11-24: 138; 2023-11-26: 124
Gravel bedding | P
Gravel bedding (7.1.2) | A | cu.m | 2023-11-08: 9.6; 2023-11-13: 12; 2023-11-22: 19.2; 2023-11-23: 12.6; 2023-11-24: 12; 2023-11-25: 19.2; 2023-11-26: -; 2023-11-29: 4.8; 2023-12-01: 4.8; 2023-12-02: 4.8
Backfilling | P
Backfilling (7.1.3) | A | cu.m | 2023-11-13: 205; 2023-11-26: 158
PVC pipe for drain hole | P
PVC pipe for drain hole (7.1.4) | A | lin.m
Gabion | P
Gabion (7.1.5) | A | cu.m
Nonwoven fabric | P
Nonwoven fabric (7.1.6) | A | sq.m
Reinforced concrete pile (400×400) | P
Reinforced concrete pile (400×400) (7.1.7) | A | lin.m
Concrete works for drainage
Formwork | P
Formwork (7.2.1) | A | sq.m | 2023-11-11: 14.5; 2023-11-13: 57; 2023-11-15: 16; 2023-11-18: 86; 2023-11-21: 130; 2023-11-22: 130; 2023-11-23: 36; 2023-11-24: 36; 2023-11-25: 72; 2023-11-26: 118; 2023-11-27: 58; 2023-11-28: 15; 2023-11-29: 15; 2023-12-01: 28; 2023-12-02: 48
Reinforcing bars | P
Reinforcing bars (7.2.2) | A | kg | 2023-11-09: 200; 2023-11-10: 200; 2023-11-11: 400; 2023-11-12: 1000; 2023-11-15: 2000; 2023-11-21: 700; 2023-11-23: 800; 2023-11-24: 800; 2023-11-25: 500; 2023-11-26: 100; 2023-11-27: 200
Dowel bars | P
Dowel bars (7.2.3) | A | kg | 2023-11-24: 538
Concrete type C (ordinary stress such as ditch, culvert etc) | P
Concrete type C (ordinary stress such as ditch, culvert etc) (7.2.4) | A | cu.m | 2023-11-10: 6; 2023-11-12: 12.96; 2023-11-16: 20; 2023-11-19: 13.5; 2023-11-20: 9; 2023-11-21: 13.5; 2023-11-22: 9; 2023-11-23: 14.4; 2023-11-24: -; 2023-11-25: 9.6; 2023-11-26: 22; 2023-11-27: 14; 2023-11-28: 15; 2023-11-29: 9; 2023-11-30: 9.5; 2023-12-02: 5.5
Concrete type G (leveling concrete) | P
Concrete type G (leveling concrete) (7.2.5) | A | cu.m | 2023-11-08: 4.8; 2023-11-14: 6; 2023-11-22: 9.6; 2023-11-23: 6.4; 2023-11-24: 6.4; 2023-11-29: 2.4; 2023-12-01: 2.4; 2023-12-02: 2.4
Adhesive water stop plate t=100mm (for concrete joint) | P
Adhesive water stop plate t=100mm (for concrete joint) (7.2.6) | A | lin.m | 2023-11-24: 44
Joint filler (for concrete joint) | P
Joint filler (for concrete joint) (7.2.7) | A | sq.m | 2023-11-24: 18
Miscellaneous metal works
Trash racks | P
Trash racks (7.3.1) | A | kg
Trap | P
Trap (7.3.2) | A | kg
Handrail | P
Handrail (7.3.3) | A | kg
Periphery road
Zone 5
Road pavement
Base course | P
Base course (8.1.1.1) | A | cu.m
Granular subbase course | P
Granular subbase course (8.1.1.2) | A | cu.m
Road furniture
Storm water drainage on the right side of the road (open). W 400x D400 | P
Storm water drainage on the right side of the road (open). W 400x D400 (8.1.2.1) | A | lin.m
Storm water drainage on the left side of the road (cover). W 400x D400 | P
Storm water drainage on the left side of the road (cover). W 400x D400 (8.1.2.2) | A | lin.m
Cover of drain, W 400 (For Heavy weight vehicle), on left side of road | P
Cover of drain, W 400 (For Heavy weight vehicle), on left side of road (8.1.2.3) | A | lin.m
Vertical drainage (with cover). W 400x400 | P
Vertical drainage (with cover). W 400x400 (8.1.2.4) | A | lin.m
Traffic signage
Traffic signage | P
Traffic signage (8.1.3.1) | A | nos
Concrete works for miscellaneous civil structures
Subbase bedding for civil structures | P
Subbase bedding for civil structures (8.1.4.1) | A | cu.m
Blinding concrete (G15) | P
Blinding concrete (G15) (8.1.4.2) | A | cu.m
Fence work
Chain-link wire fence with coiled razor wire on top | P
Chain-link wire fence with coiled razor wire on top (8.1.5.1) | A | lin.m
Zone 5
Road pavement
Base course | P
Base course (8.2.1.1) | A | cu.m
Granular subbase course | P
Granular subbase course (8.2.1.2) | A | cu.m
Road furniture
Storm water drainage on the right side of the road (open). W 400x D400 | P
Storm water drainage on the right side of the road (open). W 400x D400 (8.2.2.1) | A | lin.m
Storm water drainage on the left side of the road (cover). W 400x D400 | P
Storm water drainage on the left side of the road (cover). W 400x D400 (8.2.2.2) | A | lin.m
Cover of drain, W 400 (For Heavy weight vehicle), on left side of road | P
Cover of drain, W 400 (For Heavy weight vehicle), on left side of road (8.2.2.3) | A | lin.m
Vertical drainage (with cover). W 400x400 | P
Vertical drainage (with cover). W 400x400 (8.2.2.4) | A | lin.m
Traffic signage
Traffic signage | P
Traffic signage (8.2.3.1) | A | nos
Concrete works for miscellaneous civil structures
Casting of concrete for gravity walls | P
Casting of concrete for gravity walls (8.2.4.1) | A | cu.m
Subbase bedding for civil structures | P
Subbase bedding for civil structures (8.2.4.2) | A | cu.m
Blinding concrete (G15) | P
Blinding concrete (G15) (8.2.4.3) | A | cu.m
Maintenance of Zone 5 road
Maintenance of Zone 5 road | P
Maintenance of Zone 5 road (8.2.5.1) | A | LS
Fence work
Chain-link wire fence with coiled razor wire on top | P
Chain-link wire fence with coiled razor wire on top (8.2.6.1) | A | lin.m
Note on H9: ====== ID#AAABAoitUVw G. M. Bayazid (2023-11-15 11:46:56) No works due to political unrest!